## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | React.js
INTERN NAME: | Rushikesh Mandhare
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2024-07-29
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | Job Portal
PROJECT ID | -
INTERN NAME | Rushikesh Mandhare
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
This document outlines the test strategy, process, workflow, and methodologies used for testing the Job Portal - LinkedIn replica project. The goal is to ensure that the application meets all specified requirements and quality standards before deployment. Testing will be conducted in phases, with a focus on functional, non-functional, and integration aspects of the web application.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
Registration and Authentication: Testing user registration, login, password recovery, and profile management. Profile Section: Testing the creation, editing, and viewing of user profiles. Search Functionality: Ensuring accurate search results for users, jobs, and posts. Job Postings: Testing the ability to post, view, and apply for jobs. Notifications: Validating the accuracy and relevance of notifications. Connections: Testing connection requests, acceptances, and removals. Messaging: Ensuring the messaging feature works for sending and receiving messages. Events: Testing the creation, viewing, and joining of events. News Feed: Validating the content and display of the news feed. Postings: Ensuring user posts are correctly displayed in the news feed and notifications.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
Mobile App Testing: The project does not include testing for mobile versions or applications. Performance Optimization: Initial testing will not focus on performance optimization; this will be addressed in later phases if necessary. Third-Party Integrations: Testing of integrations with external platforms or services is not included in this phase.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
Ensure the application conforms to all functional and non-functional requirements. Verify that the application meets the quality specifications defined by the client. Identify and resolve all critical and high-priority bugs before the go-live date.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
QA Analyst: Develop and execute test cases, report bugs, and validate fixes. Test Manager: Oversee the testing process, coordinate with other teams, and ensure adherence to the test plan. Configuration Manager: Manage test environments, tools, and configurations. Developers: Fix bugs and implement enhancements based on test findings. Installation Team: Assist with deployment and installation of the application in the test environment.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
The Agile methodology will be adopted for this project due to its iterative nature, allowing for continuous feedback and improvement throughout the development cycle. Agile will facilitate flexibility and quick adaptation to changes.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
Unit Testing: Verify individual components for correctness. Integration Testing: Ensure different modules work together as expected. System Testing: Validate the complete and integrated application against the requirements. User Acceptance Testing (UAT): Confirm that the application meets the user's needs and expectations.
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Bug Resolution: Bugs will be categorized based on severity and priority. Prioritization: Critical bugs will be fixed immediately, while less severe bugs will be scheduled for resolution in future releases. Schedule: A regular review meeting will be held to update the status and schedule for bug fixes.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
Test Coverage: Ensure 100% coverage of all functional requirements. Test Execution: Complete all manual and automated test cases. Bug Fixes: All high-priority bugs are fixed, and other bugs are documented for future releases.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Test Plan: Document outlining the test strategy and scope. Test Cases: Detailed test scenarios and steps for execution. Requirement Traceability Matrix: Mapping of requirements to test cases. Bug Reports: Documentation of identified issues and their status. Test Strategy: Overview of the overall testing approach and methodology. Test Metrics: Performance metrics and results from testing.
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
Requirements Tracking Tool: Jira or similar tool for tracking requirements and test cases. Bug Tracking Tool: Bugzilla, Jira, or similar tool for managing and tracking bugs. Automation Tools: Selenium or similar tools for automating repetitive tests.
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Hardware: Windows 10 or later Minimum 8GB RAM 2GHz Processor or higher
ADDITIONAL COMMENTS
Regular meetings will be held to review progress and address any issues. All stakeholders will be kept informed about testing status and outcomes.
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Registration | Verify user registration process and data validation | 2024-07-15 | 2024-07-15 | QA Analyst | PASSED | Registration is working fine.
Profile Section | Test profile creation, editing, and viewing | 2024-07-16 | 2024-07-17 | QA Analyst | PENDING | Initial tests completed; refining UI.
Search Functionality | Validate search results for users, jobs, and posts | 2024-07-17 | 2024-07-19 | QA Analyst | PASSED | working
Job Postings | Test job posting, viewing, and application | 2024-07-20 | 2024-07-22 | QA Analyst | PASSED | working
Connections | Test connection requests and management | 2024-07-24 | 2024-07-27 | QA Analyst | PASSED | working
Postings | Ensure posts are displayed correctly in news feed | 2024-07-28 | 2024-07-29 | QA Analyst | PASSED | working
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.