## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | React.js
INTERN NAME: | Rushikesh Mandhare
PROJECT NAME: | Job Portal
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-07-12
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Job Portal |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | -
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2024-07-15 | Delays in Feature Development | Schedule | Team missing deadlines | Regular progress reviews, clear timelines | Implement agile sprints, set milestone checkpoints | Project Manager | SOLVED | Improved after implementing agile
2 | 2024-07-18 | User Interface Feedback | User Experience | Negative user feedback | Conduct regular user testing and feedback sessions | Schedule bi-weekly user feedback sessions | UX Team | SOLVED | User satisfaction increased
3 | 2024-07-18 | Server Downtime | Technical | Slow response times | Ensure robust infrastructure and monitoring | Implement load balancers, regular server maintenance | DevOps Team | SOLVED | No downtime post-implementation
4 | 2024-07-19 | Integration Issues with External APIs | Technical | Failed API calls | Regular testing of integrations | Automate API testing, maintain good provider relations | DevOps Team | OPEN | Continue monitoring
5 | 2024-07-25 | Limited Initial User Adoption | User Engagement | Low sign-up rates | Enhance marketing efforts and user onboarding | Launch marketing campaign, improve onboarding flow | Marketing Team | OPEN | Monitoring user growth