## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 0 | 1 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Job Portal |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 3 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 3 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: | 2024-07-10 | Project Team Lead: | ABC |  |  | Dependency | 3 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 12 |  |  |  |  | 1
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Data Breaches | High | Implement robust security measures (encryption, two-factor authentication) | Security Team | High | 27 (High) | Open | Risk
2 | Risk | Performance Issues with High Traffic | Medium | Optimize code, use scalable infrastructure (load balancers, CDNs) | Development Team | Moderate | 18 (Medium) | Closed | Assumption
3 | Risk | User Adoption Issues | Medium | Conduct user research and beta testing, offer tutorials and support | Marketing Team | Moderate | 16 (Medium) |  | Issue
4 | Assumption | Users have internet access | Medium | Design offline capabilities for core features | Medium | Moderate | 15 |  | Dependency
5 | Assumption | Users provide accurate profile information | Medium | Implement verification processes | Medium | Moderate | 14
6 | Assumption | Moderate initial user traffic | Medium | Plan for scalability from the start | Medium | Moderate | 16 |  | Open
7 | Issue | Delays in Development | high | Regular progress reviews, agile sprints | Project Manager | High | 30 |  | Closed
8 | Issue | Incomplete User Feedback | Medium | Regular user feedback sessions | UX Team | Moderate | 20
9 | Issue | Limited Budget | Medium | Prioritize essential features, seek additional funding | Finance Team | Moderate | 17 |  | Critical
10 | Dependency | External Job Listing APIs | high | Regularly test API integrations | DevOps Team | High | 25 |  | High
11 | Dependency | Email Service Providers for Notifications | high | Have backup email service providers | IT Team | High | 26 |  | Moderate
12 | Dependency | OAuth Providers for Authentication | high | Ensure compatibility with major providers (Google, LinkedIn) | Security Team | High | 25 |  | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24